## Work Items
Id | Summary | Children | Story Points | Filed Against | Planned For | Owned By | Time Spent | Status
956 | Implement Basic Rest client for food and Junit test |  |  | Backend Web | Backlog | Unassigned |  | New
957 | Implement Basic Rest client for device and Junit test |  |  | Backend Web | Backlog | Unassigned |  | New
1044 | Review issues found by PMD |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1045 | Review issues found by CheckStyles |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1042 | Show Logon User after login |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1036 | Drugs Datasets: Put red '*' in "Date From" and "Date To" for required fields |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1041 | Need ALT tags for logo |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1043 | Fit the chart into the screen to avoid scrolling |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1037 | Meta, keywords for the pages have not been set |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1038 | Leading space in login should not be allowed |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1039 | Put label on the x-axis of charts, even it may be easily to understand |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1040 | Please make sure "Reload Data" before you overwrite it |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1035 | After save the Drugs Datasets, the "Note:" value is erased |  |  | OPEN FDA Prototype (Change Management) | Backlog | Unassigned |  | New
1000 | Define Release Backlog |  |  | Backend Web | Sprint 0 (1.0) | Michael Chung |  | Done
1001 | Write Acceptance Criteria for all stories |  |  | Backend Web | Sprint 0 (1.0) | David Lam |  | Done
996 | Add Non-Functional User Stories including security requirements |  |  | Backend Web | Sprint 0 (1.0) | David Lam |  | Done
997 | Break features and epics into user stories |  |  | Backend Web | Sprint 0 (1.0) | David Lam |  | Done
998 | Define Release Goal and select features |  |  | Backend Web | Sprint 0 (1.0) | Michael Chung |  | Done
999 | Estimate user stories |  |  | Backend Web | Sprint 0 (1.0) | David Lam |  | Done
955 | Test Basic Rest client for drug and Junit test |  |  | Backend Web | Sprint 1 (1.0) | Wing Lo | 4 hours | Done
969 | Deploy Infrastructure as a Service (IaaS) at Amazon AWS (CAT 8) |  |  | Infrastructure | Sprint 1 (1.0) | chi au | 4 hours | Done
951 | Create MVC Project |  |  | Infrastructure | Sprint 1 (1.0) | Tit Yip |  | Done
959 | Dockerize the tomcat web server |  |  | DevOps | Sprint 1 (1.0) | Wing Lo |  | Done
980 | Create database and tables |  |  | Backend Web | Sprint 1 (1.0) | David Lam | 2 hours | Done
1003 | As a registered user, I can be authenticated as an registered user |  | 20 pts | OPEN FDA Prototype (Change Management) | Sprint 1 (1.0) | Tit Yip |  | Done
942 | Share code with GitHub Control |  |  | DevOps | Sprint 1 (1.0) | Wing Lo | 1 hour | Done
943 | Define sprints/iterations |  |  | OPEN FDA Prototype (Change Management) | Sprint 1 (1.0) | David Lam | 30 mins | Done
944 | Define categories and releases for work items |  |  | OPEN FDA Prototype (Change Management) | Sprint 1 (1.0) | David Lam | 1 hour | Done
945 | Define team members |  |  | OPEN FDA Prototype (Change Management) | Sprint 1 (1.0) | David Lam | 30 mins | Done
946 | Define permissions |  |  | OPEN FDA Prototype (Change Management) | Sprint 1 (1.0) | David Lam | 30 mins | Done
950 | Create Threat Model Analysis Report |  |  | Security | Sprint 1 (1.0) | David Lam | 2 hours | Done
947 | Set up tiles definitions for the project base |  |  | Front End Web | Sprint 1 (1.0) | Elaine Hung |  | Done
977 | Sprint 1 Code Review |  |  | Backend Web | Sprint 1 (1.0) | David Lam | 1 hour | Done
948 | Set up multiple languages for project base |  |  | Front End Web | Sprint 1 (1.0) | Elaine Hung |  | Done
962 | Setup Jenkins to run Junit tests |  |  | DevOps | Sprint 2 (1.0) | Chi Kwong |  | Done
979 | Code Review for Sprint 2 |  |  | Backend Web | Sprint 2 (1.0) | David Lam | 1 hour | Done
1015 | Configure the maven build in Jenkins |  |  | DevOps | Sprint 2 (1.0) | Wing Lo |  | Done
982 | Create JSP Page for Consuming Drugs - Adverse Drugs |  |  | Front End Web | Sprint 2 (1.0) | Tit Yip | 2 hours | Done
966 | Setup Jenkins to run code security scanning tool - Appscan Source |  |  | DevOps | Sprint 2 (1.0) | Wing Lo | 4 hours | Done
970 | Document Requirements |  |  | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | David Lam | 4 hours | Done
960 | Setup Jenkins to get source code from git |  |  | DevOps | Sprint 2 (1.0) | Chi Kwong |  | Done
941 | Define a new build in Jenkins | #961 #962 #963 #964 #965 #966 #960 |  | DevOps | Sprint 2 (1.0) | Chi Kwong | 4 hours | Done
958 | Dockerize the openFDA application |  |  | DevOps | Sprint 2 (1.0) | Wing Lo | 8 hours | Done
988 | Format JSP pages for login page |  |  | Front End Web | Sprint 2 (1.0) | Elaine Hung | 4 hours | Done
963 | Setup Jenkins to build the application with Maven |  |  | DevOps | Sprint 2 (1.0) | Chi Kwong | 2 hours | Done
967 | Dockerize the MySQL database |  |  | DevOps | Sprint 2 (1.0) | Wing Lo | 30 mins | Done
981 | Create Data Access Layer |  |  | Backend Web | Sprint 2 (1.0) | Tit Yip | 2 hours | Done
973 | Create Class Diagrams |  |  | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | David Lam | 2 hours | Done
976 | Create Controller for Consuming Drugs - Adverse Drugs |  |  | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | Tit Yip | 2 hours | Done
974 | Create Object Diagram |  |  | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | David Lam | 2 hours | Done
972 | Installation and management of open source monitoring tools (Cacti) |  |  | DevOps | Sprint 2 (1.0) | chi au | 4 hours | Done
971 | Create Wire Frame |  |  | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | David Lam | 2 hours | Done
964 | Setup Jenkins to run code analyzer tool - CheckStyle |  |  | DevOps | Sprint 2 (1.0) | Chi Kwong |  | Done
968 | Setup Jenkins to have 1st deployment environments |  |  | DevOps | Sprint 2 (1.0) | Chi Kwong | 4 hours | Done
978 | Modify the default foundation template (color, font, and components sizes) |  |  | Front End Web | Sprint 2 (1.0) | Elaine Hung | 2 hours | Done
975 | As a registered user, I can consume OpenFDA Drug Adverse Events data | #976 #982 #983 #984 #985 #989 | 20 pts | OPEN FDA Prototype (Change Management) | Sprint 2 (1.0) | Tit Yip |  | Done
949 | Install Foundation framework for the project |  |  | Front End Web | Sprint 2 (1.0) | Elaine Hung |  | Done
989 | Format JSP page for Consume OpenFDA Drug Adverse Event |  |  | Front End Web | Sprint 3 (1.0) | Elaine Hung | 4 hours | Done
995 | Open source vulnerability scanner (OpenVAS) |  |  | DevOps | Sprint 3 (1.0) | chi au | 12 hours | Done
985 | Test Consume OpenFDA Drug Adverse Events Story |  |  | QA | Sprint 3 (1.0) | Chi Kwong | 2 hours | Done
1004 | Modify OpenFDA generic pages into responsive |  |  | Backend Web | Sprint 3 (1.0) | Elaine Hung | 2 hours | Done
983 | Add graph visualization for Consuming Drugs - Adverse Drugs |  |  | Front End Web | Sprint 3 (1.0) | Tit Yip | 4 hours | Done
1005 | Insert foundation datepicker plugin (css and js) |  |  | Backend Web | Sprint 3 (1.0) | Elaine Hung |  | Done
986 | Create logout feature |  |  | Backend Web | Sprint 3 (1.0) | Elaine Hung | 4 hours | Done
961 | Setup Jenkins to deploy to a docker container p1 |  |  | DevOps | Sprint 3 (1.0) | Wing Lo | 30 mins | Done
984 | Create Unit Testing for Consuming Drugs - Adverse Drugs |  |  | QA | Sprint 3 (1.0) | Tit Yip | 2 hours | Done
990 | Code Review for Sprint 3 |  |  | Backend Web | Sprint 3 (1.0) | David Lam |  | Done
1016 | Setup Jenkins to deploy to a docker container p2 |  |  | DevOps | Sprint 4 (1.0) | Wing Lo | 8 hours | Done
1006 | Create test case/script for saving FDA data |  |  | Backend Web | Sprint 4 (1.0) | David Lam | 1 hour | Done
993 | Config PMD Jenkins plugin |  |  | Backend Web | Sprint 4 (1.0) | Chi Kwong | 2 hours | Done
1010 | Create Unit Test for saving Drugs - Adverse Events Data |  |  | Backend Web | Sprint 4 (1.0) | Tit Yip | 1 hour | Done
1014 | Code Review for Sprint 4 |  |  | Backend Web | Sprint 4 (1.0) | David Lam | 1 hour | Done
1007 | As a registered user, I can save Drugs Adverse events data | #1008 #1009 #1010 #1011 #1012 | 20 pts | Backend Web | Sprint 4 (1.0) | Tit Yip |  | Done
1011 | Format JSP page for saving Drugs - Adverse Events data |  |  | Front End Web | Sprint 4 (1.0) | Elaine Hung | 2 hours | Done
1008 | Create Controller for Saving Drugs - Adverse data |  |  | Backend Web | Sprint 4 (1.0) | Tit Yip | 2 hours | Done
1013 | Setup Jenkins to have 2nd deployment environments |  |  | DevOps | Sprint 4 (1.0) | Chi Kwong |  | Done
954 | Perform static code security scan |  |  | Security | Sprint 4 (1.0) | Wing Lo | 1 hour | Done
965 | Setup Jenkins to run code analyzer tool - PMD |  |  | DevOps | Sprint 4 (1.0) | Chi Kwong | 2 hours | Done
1009 | Create JSP Page for saving Drugs - Adverse Events Data |  |  | Backend Web | Sprint 4 (1.0) | Tit Yip | 2 hours | Done
991 | Config JaCoCo Jenkins plugin |  |  | Backend Web | Sprint 4 (1.0) | Chi Kwong | 1 hour 30 mins | Done
992 | Config Findbugs Jenkins plugin |  |  | Backend Web | Sprint 4 (1.0) | Chi Kwong | 2 hours | Done
1033 | QA test |  |  | Backend Web | Sprint 5 (1.0) | Chi Kwong | 1 hour | Done
1034 | Create Deployment Guide |  |  | Backend Web | Sprint 5 (1.0) | Wing Lo | 2 hours | Done
1018 | Create controller for modifying saved data |  |  | Backend Web | Sprint 5 (1.0) | Tit Yip | 2 hours | Done
1028 | Fix findings from dynamic scan test |  |  | Backend Web | Sprint 5 (1.0) | Tit Yip | 2 hours | Done
1019 | Create JSP page for modifying saved data |  |  | Backend Web | Sprint 5 (1.0) | Tit Yip | 2 hours | Done
1031 | Backend Bug fix after QA test |  |  | Backend Web | Sprint 5 (1.0) | Tit Yip | 4 hours | Done
1012 | Test Saving Drugs - Adverse Events Data |  |  | QA | Sprint 5 (1.0) | Chi Kwong | 2 hours | Done
1027 | Dynamic scan testing |  |  | Backend Web | Sprint 5 (1.0) | David Lam | 2 hours | Done
1020 | Create unit test for modifying saved data |  |  | Backend Web | Sprint 5 (1.0) | Tit Yip | 2 hours | Done
1029 | Perform usability test with non-developers |  |  | Backend Web | Sprint 5 (1.0) | David Lam | 2 hours | Done
1021 | Format JSP Page for modifying saved data |  |  | Front End Web | Sprint 5 (1.0) | Elaine Hung | 2 hours | Done
1030 | Test deployment guide |  |  | Backend Web | Sprint 5 (1.0) | Chi Kwong | 2 hours | Done
1017 | As a registered user, I can modify saved data | #1018 #1019 #1020 #1021 #1022 | 20 pts | Backend Web | Sprint 5 (1.0) | Tit Yip |  | Done
1032 | Frontend bug fix after QA Test |  |  | Backend Web | Sprint 5 (1.0) | Elaine Hung | 4 hours | Done
1022 | Test modifying saved data |  |  | QA | Sprint 5 (1.0) | Chi Kwong | 2 hours | Done